## Modules
Module | Total Cases | Executed | Pass | Fail | Blocked | Not Run | Execution Progress %
Admin Groups | 1 | 0 | 0 | 0 | 0 | 1 | 0
Admin Users | 2 | 0 | 0 | 0 | 0 | 2 | 0
Authentication | 2 | 1 | 1 | 0 | 0 | 1 | 50
Catalog API | 18 | 0 | 0 | 0 | 0 | 18 | 0
Customers | 3 | 0 | 0 | 0 | 0 | 3 | 0
Health API | 1 | 1 | 1 | 0 | 0 | 0 | 100
Invoices | 5 | 0 | 0 | 0 | 0 | 5 | 0
Permissions | 2 | 1 | 0 | 0 | 1 | 1 | 50
Product Import | 4 | 1 | 0 | 0 | 1 | 3 | 25
Products | 6 | 0 | 0 | 0 | 0 | 6 | 0
Public Catalog | 2 | 0 | 0 | 0 | 0 | 2 | 0
Purchases | 7 | 0 | 0 | 0 | 0 | 7 | 0
Reports | 2 | 0 | 0 | 0 | 0 | 2 | 0
Stock | 3 | 0 | 0 | 0 | 0 | 3 | 0
Suppliers | 1 | 0 | 0 | 0 | 0 | 1 | 0

## Defects
Metric | Value | Notes
Confirmed Defects | 0 | No confirmed product defects yet
Observations | 2 | Pending manual confirmation
Rejected | 0 | No rejected records yet
Severity Critical | 0 | Confirmed defect distribution only
Severity High | 0 | Confirmed defect distribution only
Severity Medium | 0 | Confirmed defect distribution only
Severity Low | 0 | Confirmed defect distribution only

## Scenarios
Scenario ID | Has Test Case | Related Test Case Count | Executed Case Count | Pass | Fail | Blocked | Not Run | Coverage Status | Notes
SCN-API-001 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | Executed | Scenario has at least one executed test case.
SCN-API-002 | Yes | 5 | 0 | 0 | 0 | 0 | 5 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-API-003 | Yes | 8 | 0 | 0 | 0 | 0 | 8 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-API-004 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-API-005 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-API-006 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-AUTH-001 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | Executed | Scenario has at least one executed test case.
SCN-AUTH-002 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-AUTH-003 | No | 0 | 0 | 0 | 0 | 0 | 0 | Gap - No Test Case | Documented scenario exists in Phase 3 but is not represented in current test case files.
SCN-CUS-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-CUS-002 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-GOV-001 | Yes | 1 | 1 | 0 | 0 | 1 | 0 | Executed | Scenario has at least one executed test case.
SCN-GOV-002 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-GOV-003 | No | 0 | 0 | 0 | 0 | 0 | 0 | Gap - No Test Case | Documented scenario exists in Phase 3 but is not represented in current test case files.
SCN-GOV-004 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-GOV-005 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-GOV-006 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-INV-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-INV-002 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-INV-003 | No | 0 | 0 | 0 | 0 | 0 | 0 | Gap - No Test Case | Documented scenario exists in Phase 3 but is not represented in current test case files.
SCN-INV-004 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-INV-005 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-INV-006 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PROD-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PROD-002 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PROD-003 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PROD-004 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PROD-005 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PROD-006 | Yes | 2 | 1 | 0 | 0 | 1 | 1 | Executed | Scenario has at least one executed test case.
SCN-PROD-007 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PUB-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PUB-002 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PUB-003 | No | 0 | 0 | 0 | 0 | 0 | 0 | Gap - No Test Case | Documented scenario exists in Phase 3 but is not represented in current test case files.
SCN-PUR-001 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PUR-002 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PUR-003 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-PUR-004 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-REP-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-REP-002 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-STK-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-STK-002 | Yes | 2 | 0 | 0 | 0 | 0 | 2 | Designed Only | Scenario is covered by design but has not been executed yet.
SCN-SUP-001 | Yes | 1 | 0 | 0 | 0 | 0 | 1 | Designed Only | Scenario is covered by design but has not been executed yet.

## Interfaces
Interface | Total Cases | Executed | Pass | Fail | Blocked | Not Run | Execution Progress %
Admin UI | 38 | 3 | 1 | 0 | 2 | 35 | 7.89
API | 19 | 1 | 1 | 0 | 0 | 18 | 5.26
Public UI | 2 | 0 | 0 | 0 | 0 | 2 | 0

## Summary
Metric | Value | Notes
Total Test Cases | 59 | UI + API combined
Executed Test Cases | 4 | Reporting Status not equal to Not Run
Pass | 2 | Real confirmed pass evidence only
Fail | 0 | Confirmed product defects only
Blocked | 2 | Automation Script Failure normalized to Blocked for summary reporting
Not Run | 55 | Still pending real execution
Execution Progress % | 6.78 | Executed / Total test cases
Pass Rate On Executed % | 50 | Pass / Executed
Fail Rate On Executed % | 0 | Fail / Executed
Blocked Rate On Executed % | 50 | Blocked / Executed
Scenario Count In Phase 3 | 42 | Scenario source of truth from test-scenarios.md
Scenarios Mapped To Test Cases | 38 | Distinct scenario IDs represented in UI/API case files
Scenario Design Coverage % | 90.48 | Mapped scenarios / documented scenarios
Executed Scenarios | 4 | Distinct scenarios with at least one executed test case
Scenario Execution Coverage % | 9.52 | Executed scenarios / documented scenarios
Confirmed Defects | 0 | No confirmed product defects as of 2026-04-05
Observations | 2 | Needs manual confirmation before issue creation